Gant Chart and Network Diagram

Determine time estimates and calculate the expected completion time for each activity

| ACTIVITY | TIME ESTIMATE (In days) o r p |  |  | EXPECTED TIME (ET) o+4r+p6 |
| --- | --- | --- | --- | --- |
| - Project Initiation - Feasibility Analysis - Requirements Gathering - Financial Module Analysis - Process Modeling - Database Schema Design - Auto-Restock Alert UI Design - Financial Logic Design - Module Development - System Testing - Final Documentation | 3 3 6 5 6 8 6 6 15 7 5 | 5 5 8 7 9 10 8 8 19 9 7 | 7 7 10 9 12 12 10 10 23 11 9 | 5 5 8 7 9 10 8 8 19 9 7 |

Determine the sequence of the activities and precedence relationships among all activities by

constructing a Gantt chart and network diagram

| ACTIVITY | PRECEDING ACTIVITY | EXPECTED TIME (ET) o+4r+p6 |
| --- | --- | --- |
| - Project Initiation - Feasibility Analysis - Requirements Gathering - Financial Module Analysis - Process Modeling - Database Schema Design - Auto-Restock Alert UI Design - Financial Logic Design - Module Development - System Testing - Final Documentation | - 1 2 3 4 5 6 4 7,8 9 10 |  |
|  |  | 5 5 8 7 9 10 8 8 19 9 7 |

TE=38

TL=38

ET=7

ET=9

ET=19

ET=8

ET=10

ET=8

ET=9

1 →2 → 3→ 4→5→6→ (7,8) →9→10→11

Noncritical Path

Critical Path

ET=7

ET=8

TE=71

TL=71

TE=63

TL=63

TE=45

TL=45

TE=45

TL=45

ET=5

TE=29

TL=29

TE=21

TL=21

TE=15

TL=15

TE=8

TL=8

ET=5

TE=4

TL=4

TE=77

TL=77

# Network Diagram

[11]

Final Documentation

[10]

System Testing

[9]

Module Development

[8]

Financial Logic Design

[7]

Auto-Restock Alert UI Design

[6]

Database Schema Design

[5]

Process Modeling

[4]

Financial Module Analysis

[3]

Requirements Gathering

[2]

Feasibility Analysis

[1]

Project Initiation

| ACTIVITY | TE | TL | SLACK TL-TE | ON CRITICAL PATH |
| --- | --- | --- | --- | --- |
| 1 2 3 4 5 6 7 8 9 10 11 | 4 8 15 21 29 38 45 45 63 71 77 | 4 8 15 21 29 38 45 45 63 71 77 | 0 0 0 0 0 0 0 0 0 0 0 | ✓ ✓ ✓ ✓ ✓ ✓ ✓ ✓ ✓ ✓ |